Specification

Faith Alliance – Youth Work, Mentoring and Youth Leadership Training

Contents

1 About the West Midlands Violence Reduction Partnership (WMVRP)	1

2 About the West Midlands Faith Alliance	2

2.1 Introduction	2

2.2 Work to date	2

2.3 Faith Alliance Projects for 2024-25	3

3	Vision for Youth Work, Mentoring and Youth Voice in Faith Spaces	3

3.1 Overall Project Requirements for Youth Work, Mentoring and Young Leaders	4

3.2 Expectations of providers	5

3.3 Investment over the course of the project	5

3.4 Expected outcomes & impact and Performance Monitoring	5

3.5 Required standards and skills to be an Approved Provider	7

3.6 Project Timescales and Implementation	7

4 Scoring Criteria and decision process	7

5 Contact for any queries	9

## 1 About the West Midlands Violence Reduction Partnership (WMVRP)

The West Midlands Violence Reduction Partnership (WMVRP) aims to reduce violent crime across the West Midlands region. It benefits from the expertise of partners in public health, criminal justice, sports, education, and policing in order to take on a collaborative approach towards reducing violence. Violence and the causes of violent acts are complex and multi-layered. Tackling the root causes is not straightforward. It takes time and cooperation between organisations with a shared will.

There is a long history of commitment to ending violence across the West Midlands. In 2015 the Violence Prevention Alliance was established. Funded by the Police and Crime Commissioner it saw Public Health England work with West Midlands Police and others to tackle the causes of violent behaviour; an acknowledgement that simply making more arrests on the streets would not solve our problem.

The VRP adopts a public health approach to violence. This means thinking about violence in the same way that medical professionals consider the spread of diseases.

It means focusing on understanding the root causes of the problem and on testing, evaluating and upscaling interventions.  Developing stronger data and analysis about the problem is key to working in this way.

The 5 main strands to the VRP’s work include, supporting:

- Communities and professionals to work together

- Interventions to prevent violence

- The use of evidence to inform decisions

- Leaders to connect around a shared long-term ambition

- Production of guidance, advice and toolkits

WMVRP takes a life course approach, ensuring interventions and support to prevent violence is available at each life stage. The image below details the support we provide.

## 2 About the West Midlands Faith Alliance

### 2.1 Introduction

The West Midlands Faith Alliance (FA) is a multi-faith and community-led regional network that exists to equip, enable and empower communities of all faiths and none across the West Midlands to better understand and prevent violence, particularly violence affecting young people.

The FA seeks to address violence and associated issues in the West Midlands by utilising and promoting faith-based approaches that consider faith and participation in a faith community as potential protective factors against violence and exploitation. The FA also explores how faith-based perspectives and approaches may intersect with and complement a public health approach to tackling violence. The FA will work towards establishing a community-led movement across the West Midlands, and will seek to inspire others to do similar work in other parts of the country.

### 2.2 Work to date

Founded in 2019, the FA network has undergone significant growth in membership and reach, particularly since the easing of lockdown restrictions in 2021. Much of this earlier work was focussed on networking and developing new resources, including the pioneering Toolkit for Faith Communities in July 2022. As a result, the network now has over 460 members, consisting of faith-based organisations, places of worship, statutory partners and many others from across the West Midlands and beyond.

Since early 2023, emphasis has been placed on developing a long-term strategy for the Faith Alliance, that identifies key priorities and delivers more faith-based violence reduction projects on the ground. Determined to ensure that the strategy was co-produced with young people and communities, several months of consultation were undertaken, leading to the publication of a three-year Strategy in November 2023, complete with Action Plans in May 2024.

### 2.3 Faith Alliance Projects for 2024-25

The VRP has committed £100,000, over the 2024/2025 financial year, to help put Year 1 of the FA’s Strategy into practice. The majority of this budget (£85,000) will be spent on three youth-facing projects, each identified as priorities by the co-produced Action Plans. As outlined below, the three projects, although independent grants, are designed to complement and support one another:

#### Youth Spaces (see separate specification)

This project will pilot three new multi-faith youth spaces, utilising the shared assets and resources of local faith communities to provide spaces where young people can be safe and access positive opportunities after school. £60,000 has been allocated for this project split £20,000 per pilot youth space.

#### Youth Work, Mentoring and Youth Leadership Training (this specification)

This project is split into two parts the first will establish a new training pathway for responsible adults from across diverse faith communities to be trained in youthwork principles and good practices, and so become volunteer mentors for young people. £10,000 has been allocated for this project.

The second part will develop a young leadership training programme to equip emerging faith leaders and to enable them to be advocates of violence reduction in their respective communities. £15,000 has been allocated for this project.

## Vision for Youth Work, Mentoring and Youth Leadership Training in Faith Spaces

This is an opportunity to apply for a grant of up to £25,000 funded through West Midlands Violence Reduction Partnership, to develop the work of the regional Faith Alliance by creating more mentors and young leaders across the Faith Alliance.

The need for more people trained and equipped to engage, work with and support young people and the need to support young leaders of the future was highlighted frequently during the Faith Alliance’s consultations. Training was specifically mentioned as an area which young people and responsible adults and volunteers could access which would not only develop them personally, but would make them more of an asset to young people and the communities they serve.

Positive role models and mentors in communities make a huge difference to children and young people, and can support Faith settings in working effectively with a broader cross-section of the community. Youth work offers young people safe spaces to explore their identity, experience decision-making, increase their confidence & develop inter-personal skills. Youth work promotes values of inclusion, mutual respect, equality and trust.

Youth work itself is a qualified profession, but the skills underpinning the delivery of high-quality youth work are invaluable to support Faith settings in:

- How to engage and connect with young people

- How to coach and mentor

- How to create leaders at a young age

- How to effectively communicate with young people

- How to make an impact with young people through training in youth work principles

This project will support the Faith Alliance to:

- Develop a strong network

- Achieve the objectives within the 3-year regional Faith Alliance strategy

- Strengthen motivation and engagement with the Faith Alliance

- Expand knowledge sharing

- Develop a strong culture of learning and best practice within the Faith Alliance

### 3.1 Overall Project Requirements for Youth Work, Mentoring and Young Leadership Training

Deliver a dual focused project that will embed the following training into settings across the Faith Alliance including the Youth Spaces for adults and young people:

Adults

- Safeguarding

- Effective Communication

- Coaching and Mentoring Principles

- Advice and Guidance

- Effective Listening

- Effective Engagement

- Accessing Support for Children and Young People in the Community

Young People

- Youth Leadership Skills and Knowledge

- Public Health Approach to Violence Prevention and Reduction

- Effective Planning around Youth Leadership

- Developing Violence Prevention and Reduction Plans

It is required that you develop a delivery plan alongside the Faith Alliance Executive Group and the VRP project lead. Once this plan has been signed off by both, delivery will commence.

Work with the VRP and FA to recruit young people and adults from the Faith Alliance to join the project.

Make training/resources available, and deliver both online and in-person training sessions, to be agreed with FA Executive Group and VRP.

You will be required to provide a certificate and ongoing support to all volunteer mentors trained/mentors trained, and young leaders who go on to utilise the training.

Provide opportunities, through performance monitoring and potential external evaluation, to build the evidence base for faith-based approaches to violence reduction.

The training is to be culturally sensitive and inclusive of all faiths

### 3.2 Expectations of providers

- The provider will be an experienced in training volunteers and demonstrate understanding of culture and faith

- It is expected that the successful provider will be an organisation who can support, manage training for adult volunteers and young leaders.

- Understand that the training is not to be used to promote a particular faith or belief system, but exist for the development and learning of those attending the training, regardless of faith.

- Make use of the VRP’s training offers to enhance knowledge, information and understanding of contextual issues.

- Demonstrate their understanding of the assets, demographics, opportunities and challenges of their local neighbourhood.

- Develop a plan alongside the FA Executive Group and the VRP for the agreed training for both sets of recipients and agree the milestone plan for deliver.

## Investment over the course of the project

- The VRP have invested  up to £25,000 to cover the costs of both the training program with adult mentors and the young leaders programme, to be delivered during the 2024/2025 financial year.

- Payment terms are 30 days payment, quarterly in arrears. Payment will be made on satisfactory monitoring as per section 3.4;

- Investment is for the period August 2024 – 31 March 2025

- The successful organisation will sign up to the WMOPCC’s Grant terms and conditions which is available to view with the application pack.

## Expected outcomes & impact and Performance Monitoring

Quarterly reporting will be due on the 10th day after (financial) quarter end on:

- Progress against project outcomes, measures and targets (see table 1 below);

- Progress on contribution to the wider Faith Alliance Impacts;

- Narrative on trends and achievements, barriers and risks;

- Describe actions taken to mitigate risks;

- Actual budget spend in relation to forecast spend.

| Outcome | Measure | Target |
| --- | --- | --- |
| - Volunteer mentors trained and equipped in youth work principles | - Number of volunteer mentors trained - Volunteer mentors report increased confidence to engage with young people of all faiths and non - Measured through feedback and evidence through qualitative reports | - 30 volunteers trained across the region (minimum) |
| - Young people trained and equipped to be leaders in Faith spaces around violence prevention and reduction | - Number of young people trained - Youth Leaders report increased skills, knowledge and confidence to be a Youth Leader - Young Leaders report increased knowledge on violence reduction and approaches - Development of community violence prevention plans led by young people following on from the training | - 10 Young Leaders trained (minimum) with a further 200 young people (minimum) benefiting from the leadership of these young leaders in their Faith spaces. Young leaders are able to complete simple online forms that populate a dashboard to demonstrate the reach and impact of training. - Development of 3 community violence prevention plans led by the young leaders, supported by the tools provided during the training and the FA and VRP |
| - Good coverage of volunteer mentors across the West Midlands | - Volunteers from each local authority who will deliver across the region - Volunteers from the Safe Spaces are able to engage in the training | - Bham – 8 - Solihull – 4 - Coventry – 4 - Wolves – 4 - Sandwell – 4 - Walsall – 3 - Dudley – 3 (VRP will support with recruitment from across the region) |
| - High standard of training delivered | - Feedback from young people who have accessed mentoring - Feedback from those who have been trained | - All feedback forms to be ‘good’ or above in responses |

Table 1

Wider impacts (taken from Faith Alliance Theory of Change)

- The prevalence of violence is reduced

- Fewer young people in the criminal justice system

- Faith communities are engaged, compassionate and resilient

- The Faith Alliance is self-sustaining, with community-led activity at its core

- Long-term investment of funds, time and commitment to faith-based approaches

- Increased inter-faith collaboration on social issues of common concern

- Better partnership working between faith communities and local authorities

### 3.5 Required standards and skills to be an Approved Provider

#### Staff qualifications/skills/experience

All organisations who deliver this training will need to demonstrate:

- Strong understanding of safeguarding and issues affecting young people (all staff and volunteers must attend local authority’s safeguarding training)

- Any staff and volunteers must be over 18 and safely recruited, including completing an Enhanced DBS check and submitting two suitable references.

- Experience of delivering quality training sessions in community settings

- Commitment to being a trauma-informed organisation (for example, by attending the VRP’s Trauma-Informed Practice training)

- Commitment to the mission and values of the Faith Alliance

#### Policy requirements

Organisation(s) who deliver the Youth Work and Young Leaders training must:

- Have a current safeguarding policy and procedure that has been reviewed in the last 12 months, and that all staff and volunteers are familiar with

- A policy as an employer to comply with statutory obligations under the Equality Act 2010

- National Living Wage Employer Policy

### 3.6 Project Timescales and Implementation

| Task | Anticipated Completion Date |
| --- | --- |
| Closing date for receipt of proposals to SUMS online platform Proposals received after the deadline stated or not properly completed will be disregarded. | Deadline Monday 8th July 2024 at 5pm |
| Complete analysis of proposals against pre-agreed criteria. | Monday 15th July 2024 |
| Award Grants | w/c 29th July 2024 |
| Project Commencement Date | ASAP thereafter |

## 4 Scoring Criteria and decision process

There is an online application form to help evaluators decide which provider to fund.  The application will be worth 100% and will be scored according to how the requirements of this specification have been met.

All applications will undergo an initial sifting process to ensure they are eligible for the funding they are applying for.

Applicants will hear whether they have been successful week commencing 22nd July. Successful applicants should look to commence project delivery as soon as possible thereafter.

| # | Question No | What the evaluator is looking for | Weighting |
| --- | --- | --- | --- |
| 2 | Outline your proposal to deliver the Youth Work Training element of the Project | Demonstration of: what approaches you will take in training delivery (online/face to face) and what time commitment the participants will need to give; what training content and methodology will be used; what certification the participants be expected to receive; how you will successfully maximise the attendance of the training with participants across the region; how you will support volunteers going forward in their roles. | 25% |
| 3 | Outline your proposal to deliver the Youth Leadership Training element | Demonstration of: what approaches you will take in training delivery (online/face to face) and what time commitment the participants will need to give; what training content and methodology will be used; what certification the participants can be expected to achieve; how you will successfully fill the training with participants across the region; how you will support youth leaders going forward in their roles. | 25%% |
| 4 | Demonstrate your organisation's experience to deliver the training | Demonstration of: relevant training with volunteers and young people; understanding of culture and faith; relevant training delivered around the theme of serious violence prevention any industry qualifications/accreditations to show competency in training delivery; | 20% |
| 5 | How will you ensure your training meets the expected outcomes? | Demonstration of: Methodology to track individual outcomes of training participants use of feedback forms, session plans, registers, planning meetings, consultation with community on training, appropriate numbers of volunteers attending. commitment to returning the monitoring so the evidence can be built. | 20% |
| 6 | What will your approach be to meet the needs of other stakeholders throughout the project? | Demonstration of: Ability to work with other key partners across the region such as Faith Alliance members and executive, the Violence Reduction Partnership. Ensuring interfaith work is prioritised | 10% |

The evaluators use the following to score your applications:

| Score | Scoring Principles |
| --- | --- |
| 0 | Rejected – the question is not answered or the response is completely unacceptable |
| 1 | Very Poor response – Only partially answers the requirement with major deficiencies and little relevant detail proposed |
| 2 | Poor response – only partially acceptable with deficiencies apparent. Some evidence provided but response falls short of providing full confidence in the approach/solution described |
| 3 | Acceptable Response – meets all or most requirements but limited and/or could have been expanded upon further. Any weaknesses can be addressed. |
| 4 | Good response- Meets all requirements fully. Good level of detail, response provides high levels of assurance in relation to the proposal. |
| 5 | Excellent response – Exceeds requirement in some or all areas. Comprehensive responses demonstrating a detailed understanding of requirement and/or customer. No weaknesses noted. |

## 5 Contact for any queries

If you have any questions about the application please email vrp@westmidlands.police.uk